## Hoja1
Tasks | Assigned to | Estimation time | Total hours |  | Total estimation time | Total hours
Camera movement | Adria Avila | 1 hour | 2 hours | Martí | 21 hours | 27 hours
Player 2 movement | Adria Avila | 30 minutes | 30 minutes | Juan | 14 hours | 20,5 hours
Players movement limits | Adria Avila | 3 hours | 1 hour | Adria | 11,5 hours | 17 hours
UI Counter | Adria Avila | 1 hour | 2 hours | Xavier | 8,5 hours | 13 hours
Selection Screen | Adria Avila | 1 hour | 3 hours
Input update multiple players | Adria Avila | 30 minutes | 3 hours
Start Game Animations | Adria Avila | 3 hours | 4 hours
Intro animations | Adria Avila | 30 minutes | 30 minutes
Update Win/Lose scenes | Adria Avila | 1 hour | 1 hour
Blocking Camera | Xavier Trillo | 0 hours and 15 minutes | 0 hours and 30 minutes
Basic Movement | Xavier Trillo | 1 hour and 30 minutes | 2 hours
Smoth Animations | Xavier Trillo | 0 hours and 30 minutes | 1 hour
Collision Boxes | Xavier Trillo | 0 hours and 30 minutes | 0 hours and 30 minutes
Neutral Jump Smooth | Xavier Trillo | 0 hours and 30 minutes | 0 hours and 45 minutes
Back and Forw Jump | Xavier Trillo | 1 hour | 1 hour and 45 minutes
Scene switching | Juan Hernández | 1 hour | 1 hour
Game transcitions | Juan Hernández | 2 hours | 1 hour and 30 minutes
Updated Camera movement and reset camera | Juan Hernández | 1 hour and 30 minutes | 3 hour
Death animation | Juan Hernández | 2 hours | 4 hours
Updated Win / Lose ocndition with Dead conditions | Juan Hernández | 2 hours | 1 hour and 45 minutes
Added multiple round reset system | Juan Hernández | 30 minutes | 1 hour
Added Jump punch animations | Juan Hernández | 1 hour | 1 hour and 30 minutes
Health Bars | Juan Hernández | 1 hour | 2 hours and 15 minutes
Added multiple sounds | Juan Hernández | 3 hours | 4 hour and 15 minutes
Audio Module | Martí Torres | 3 hours | 5 hours
Collisions Boxes for attacks | Martí Torres | 2 hours | 2 hours
Remake Player 2 movement with states and inputs | Martí Torres | 3 hours | 2 hours and 30 minutes
Added reset player sistem for multiple rounds | Martí Torres | 1 hours | 30 minutes
Win / lose Conidtion | Martí Torres | 1 hour | 2 hours
flipped animations for player 2 | Martí Torres | 2hours | 1 hour and 45 minutes
Fixed neutral punch jump animation | Martí Torres | 30 minutes | 45 minutes
Fixed Scene transcitions | Martí Torres | 30 minutes | 30 minutes
Collisions cases for movement and attacks | Martí Torres | 1 hour | 2 hours
Added damage | Martí Torres | 1 hour | 3 hours
Round points | Martí Torres | 30 minutes | 30 minutes
Module Font | Martí Torres | 2 hours | 2 hours
Jump punch | Martí Torres | 1 hour and 30 minutes | 3 hours